## Info
Budget used vs. sprint completion
Sprint [list features] | Planned Budget ($) | Spent Budget ($) | Budget Used (%) | Sprint completion (%) | Status
| 1200 | 1050 | 87.5% | 90% | Good
| 700 | 720 | 102.9% | 100% | Bad
| 500 | 420 | 84% | 75% | Bad
| 900 | 420 | 46.67% | 100% | Good
| 350 | 280 | 80% | 50% | Bad
Overall | 3650 | 2890 | 79.18% | 88.49% | Good
Overall Remaining Days vs. Planned Days to Date | [5 empty] | Bugs to Fix vs. Resolved Bugs
Sprint [list features] | Planned Days | Spent Days | Status | Remaining Days |  | Sprint [list features] | Total Bugs | Resolved Bugs | Remaining Bugs
| 20 | 14 | Good | 6 |  |  | 200 | 150 | 50
| 12 | 13 | Bad | -1 |  |  | 792 | 792 | 0
| 10 | 11 | Bad | -1 |  |  | 422 | 339 | 83
| 8 | 6 | Good | 2 |  |  | 608 | 522 | 86
| 4 | 3 | Good | 1 |  |  | 120 | 108 | 12
Overall | 54 | 47 | Good | 7 |  | Overall | 2142 | 1911 | 231
Overall Earned Value
Sprint [list features] | Earned ($) | Spent ($) | Cumulative Earned ($) | Cumulative Spent ($)
| 1112 | 1050 | 1112 | 1050
| 689 | 720 | 1801 | 1770
| 0 | 420 | 1801 | 2190
| 589 | 420 | 2390 | 2610
| 302 | 280 | 2692 | 2890
Tired of working with reports manually? Status.net is a modern solution to share regular reports and gather insights automatically.
Status.net collects data regularly with scheduled auto reminders. Run powerful reports with export and print features.
Click here to try it now for free.
Automate your reporting with status.net

## Risks
Risk | Likelihood | Impact | Place in Matrix | Mitigation | Cost of Mitigation ($) | --Impact-> | 5 | 5 | 10 | 15 | 20 | 25
| 5 | 2 | 10 |  | 1,200 per month |  | 4 | 4 | 8 | 12 | 16 | 20
| 1 | 5 | 5 |  | 500 |  | 3 | 3 | 6 | 9 | 12 | 15
[7 empty] | 2 | 2 | 4 | 6 | 8 | 10
[7 empty] | 1 | 1 | 2 | 3 | 4 | 5
[8 empty] | 1 | 2 | 3 | 4 | 5
----Likelihood--->
Column D is calculated according to the input in columns B and C
Tired of working with reports manually? Status.net is a modern solution to share regular reports and gather insights automatically.
Status.net collects data regularly with scheduled auto reminders. Run powerful reports with export and print features.
Click here to try it now for free.
Automate your reporting with status.net